## Project Plan & Gantt Chart
Task ID | Phase / Task Name | Assignee | Start Date | End Date | Status | Oct W4 | Nov W1 | Nov W2 | Nov W3 | Nov W4 | Dec W1
1 | Project Planning & Proposal | Elsayed | 2026-10-25 | 2026-10-31 | In Progress | ███
2 | Requirements Gathering | Assem & Mohammed | 2026-10-25 | 2026-10-31 | In Progress | ███
3 | System Analysis & Design | Omar & Yousef | 2026-11-01 | 2026-11-06 | Not Started |  | ███
4 | M1: Data Simulation & Ingestion | Osama & Elsayed | 2026-11-07 | 2026-11-12 | Not Started |  |  | ███
5 | M2: Batch ETL Pipeline | Assem & Mohammed | 2026-11-10 | 2026-11-20 | Not Started |  |  | ███ | ███
6 | M3: Streaming Pipeline & Alerts | Omar & Yousef | 2026-11-15 | 2026-11-25 | Not Started |  |  |  | ███ | ███
7 | M4: Dashboard & Reporting | Osama & Assem | 2026-11-20 | 2026-11-28 | Not Started |  |  |  |  | ███
8 | Testing & Bug Fixing | All Team | 2026-11-25 | 2026-11-30 | Not Started |  |  |  |  | ███
9 | Final Presentation & Repo | Elsayed | 2026-12-01 | 2026-12-04 | Not Started | [5 empty] | ███